## Project Overview
Project Title
Smart Construction Site Coordination System (SCSCS)
Project Summary
The Smart Construction Site Coordination System (SCSCS) is a web-based platform designed to improve coordination, scheduling, risk management, and progress reporting on construction sites. The system provides a centralized environment where project managers, site engineers, and subcontractors can plan tasks, monitor schedules, report risks, and track project progress. The primary objective of the project is to reduce delays, improve communication among stakeholders, and support effective project management practices throughout the construction lifecycle.
Problem Statement
Construction projects frequently experience delays, cost overruns, and coordination problems due to fragmented communication and the lack of a unified system for managing daily site activities. Tasks are often tracked manually or through disconnected tools, which makes it difficult to clearly define responsibilities, monitor progress in real time, and identify potential risks at an early stage. As a result, issues such as late material deliveries, overlapping work activities, and unreported site risks are discovered too late, negatively impacting project performance.
Proposed Solution
The Smart Construction Site Coordination System addresses these challenges by providing a structured digital platform that integrates task management, schedule tracking, risk management, and progress reporting into a single system. By breaking construction activities into work packages and tasks, assigning clear responsibilities, and enabling real-time progress and risk reporting, the system improves transparency and decision-making. Weekly progress reports and risk monitoring features support proactive management and help minimize delays and coordination issues on site.
Project Scope and Focus
This project focuses on applying core project management principles—project planning, schedule management, risk management, and progress reporting—within a realistic construction site scenario. The system is developed as a functional prototype to demonstrate these concepts rather than as a full-scale commercial solution.

## Group Members
Name | Role | Main Responsibilities
Saleem Alhabachi | Project Manager & Documentation Lead | Planning, Jira management, reporting, Excel, README
Waleed | Backend Developer | Database design, backend logic, task & risk management APIs
Mohammed | Frontend Developer & QA | UI development, testing and validation

## Project Timeline
Week | Planned Activities | Responsible
Week 1 | Project planning, requirement analysis, Jira setup | All / PM Lead
Week 2 | System design, database design | Backend & Frontend
Week 3 | Task & schedule management development | Backend & Frontend
Week 4 | Risk management module development | Backend & Frontend
Week 5 | Progress reporting, testing, bug fixing | All Members
Week 6 | Documentation, final review | Project Manager

## Budget Planning
Resource | Estimated Time (Hours) | Responsible
Project Management | 30 | Project Manager
Backend Development | 80 | Backend Developer
Frontend Development | 70 | Frontend Developer
Testing & QA | 30 | Frontend Developer / All
Documentation | 20 | Project Manager

## Risk Management
Risk Description | Category | Probability | Impact | Mitigation Action
Task delays due to poor coordination | Schedule | Medium | High | Weekly progress review using Jira
Material delivery delay | Schedule | Medium | High | Early supplier follow-up and buffer time
Unclear task responsibilities | Management | Low | Medium | Clear task assignment and role definition
Technical issues during development | Technical | Medium | Medium | Early testing and code reviews